## DAYS VS ASSIGNED TO
Row Labels | Count of Assigned to | Sum of Days Required
Budget Analysis | 1 | 22
Bug Fixes | 1 | 31
Campaign Analysis | 1 | 25
Certification Programs | 1 | 30
Client Advisory | 1 | 25
Client Meetings | 1 | 20
Code Review | 1 | 30
Conference Management | 1 | 20
Content Creation | 1 | 14
Contract Negotiation | 1 | 35
Customer Feedback | 1 | 30
Data Collection | 1 | 32
Employee Training | 1 | 27
Event Planning | 1 | 25
Facility Maintenance | 1 | 20
Feature Enhancement | 1 | 34
Financial Reporting | 1 | 21
Inventory Management | 1 | 25
Inventory Optimization | 1 | 20
Investment Planning | 1 | 25
Lead Generation | 1 | 60
Manufacturing | 1 | 47
Market Expansion | 1 | 32
Market Research | 1 | 13
Market Trends Analysis | 1 | 23
Packaging Design | 1 | 22
Process Optimization | 1 | 30
Product Design | 1 | 25
Prototype Development | 1 | 18
Prototype Testing | 1 | 27
Quality Assurance | 1 | 10
Quality Control | 1 | 27
Research Paper Writing | 1 | 27
Service Improvement | 1 | 22
Skill Development | 1 | 22
Social Media Planning | 1 | 22
Software Development | 1 | 36
Software Updates | 1 | 22
Sponsorship Coordinatio | 1 | 35
Strategic Planning | 1 | 35
Supply Chain Management | 1 | 25
System Integration | 1 | 22
Technical Support | 1 | 25
Ticket Resolution | 1 | 25
Transportation Planning | 1 | 30
User Interface Design | 1 | 25

## PROJECT REPORT
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
                PROJECT REPORT
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## PROGRESS
Row Labels | Sum of Progress
Aaron | 100%
Alice | 78%
Bella | 0%
Bob | 100%
Calvin | 40%
Charlie | 45%
Daisy | 0%
Diane | 0%
Edward | 0%
Ethan | 100%
Fiona | 138%
Gabriel | 0%
Gary | 0%
Hannah | 100%
Helen | 0%
Ian | 100%
Isaac | 80%
Jane | 0%
Julia | 0%
Kevin | 10%
Kyle | 0%
Laura | 30%
Mark | 178%
Mike | 0%
n Nancy | 0%
Nathan | 50%
Olivia | 0%
Oscar | 50%
Patricia | 100%
Peter | 0%
Quentin | 0%
Quinn | 100%
Rachel | 20%
Sam | 0%
Tim | 30%
Tom | 0%
Ursula | 0%
Victor | 0%
Wendy | 70%
Xavier | 78%
Yvette | 0%
Zoe | 100%

## ASSIGNED
Row Labels | Count of Assigned to
Consulting | 3
Customer Svc | 3
Development | 3
Engineering | 3
Events | 3
Financial | 3
Logistics | 3
Marketing | 4
Operations | 3
Product Dev | 3
Production | 3
Research | 3
Sales | 3
Support | 3
Training | 3
Grand Total | 46

## PROJECT DETAILS
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%